## Review_Record
Defect Logging sheet Note: Please do not delete any rows/cells | [7 empty] | Update to Database | Administartive Information | [7 empty] | PHGCA47CAT | SE-IN-35MS | 24 |  | 3 |  | 12 |  | 4 |  | 3 |  | 7 | Clarified | Passed | Not Applicable | 1
Name Of Author : Deepthi |  |  |  | Review Date * |  |  | 2015-08-06 |  |  |  | Closing remark | [5 empty] | CAT 4.x | SE-IN-3906 |  | 1 | Defect | 11 | Build/Package/Merge | 14 | Requirements Analysis | 26 | Missing | 101 | Requirements - Missed / Incomplete / Misunderstanding | Closed | Passed with Modification |  | Not Applicable | Not Applicable | 0 | 0 | 0 | 0 | 0 | 0 | 0
Work product name / Title: Consumer Care |  |  |  | Size * | [6 empty] | Authorized Signatory |  | Co-ordinator (Sign.) |  |  |  | Document | PIC |  | 2 | Investigate | 12 | Documentation | 15 | Top Level Design | 27 | Extraneous | 102 | Lack of Communication and Sync | Duplicated | Re-Review |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Version :* |  |  |  | Review Result * |  |  |  | Passed with Modification |  |  | Remarks | [5 empty] | 2012-12-17 |  |  | 3 | Suggestion/Wishful Thinking | 56 | Initialization | 16 | Component Design | 28 | Incorrect | 103 | Incomplete Design / Impact Analysis | Hold |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reviewer(s): Deepthi Shivakumar |  |  |  | Defect density * |  |  |  | 0 | [8 empty] | 4 | CL8MUHD2 |  |  |  | 108 | Logic / Algorithm / Computation Error | 17 | Implementation |  |  | 104 | Lack of Domain Knowledge | Open |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Causal Analysis | [16 empty] | 0.5 |  |  |  |  | 109 | Error Checking / Unhandled Exception / Failure Mode |  |  |  |  | 105 | Implementer Oversight / Cover Last Mile | Rejected |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | 1 |  |  |  |  | 110 | Timing / Synchronization |  |  |  |  | 106 | Lack or Improper Usage of Standards / Conventions | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Summary of Comments | [16 empty] | ICAP-PF.0003667 |  |  |  |  | 111 | Memory Management |  |  |  |  | 107 | Lack of Re-use | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Defects |  |  |  | 0 | [12 empty] | Kooloth, Sreenath |  |  |  |  | 112 | Usability / GUI | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Investigates |  |  |  | 0 | [9 empty] | . |  |  | Internal |  |  |  |  | 113 | Design / Interface | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Suggestions/ Wishful Thinking |  |  |  | 0 | [12 empty] | 2012-12-17 |  |  |  |  | 114 | Performance / Scalability
Sl. No. * | Page | Line No. | Reviewer | Description of Comment * | Severity | Release # | Owner | Comment Type * | Defect Type | Phase of Origin | Defect Qualifier | Cause of Defect | Status | Remarks | Feedback |  | Requirements Analysis |  |  |  |  | 115 | Functionality / Workflow
1 | Utils | 61 | Deepthi | Activity context or activity is not necessary to take telephony manager. Use application context from configurationManager. |  | R2 | Naveen | [5 empty] | Closed | Saparate dedicated receiver is added to get ConnectionChanges. + Need to check by removing receiver in Manifest File |  |  | CODE1\300227886
2 | Utils | 54 | Deepthi | isEmpty() method does not make sense, inline the method. |  | R2 | Naveen | [5 empty] | Closed | Removed from the Utils.java & added inline.
3 | Utils |  | Deepthi | isTablet () and isNetworkConnected- Use application context from configurationManager. |  | R2 | Naveen | [5 empty] | Closed | Replaced with ApplicationContext from Activity parameter.
4 | Utils |  | Deepthi | In general, it seems to be a network utility, rename, don’t mix functionalities . Remove commented out. |  | R2 | Naveen | [5 empty] | Closed | Naming convention followed.
5 | CallFeature |  | Deepthi | This is reduntant and useless and remove comparision code used in unit test case (DigitalCareActivityTest,java) |  | R2 | Naveen | [5 empty] | Closed | Removed the testcases developed with reference to the class coverge report.
6 | DeviceType |  | Deepthi | This is reduntant and not used, pls remove this class. |  | R2 | Naveen | [5 empty] | Closed | Removed the redundant method successfully.
7 | DigitalCare_Config.xml |  | Deepthi | Adapting new config file changes and no extra changes should be seen except hamburger menu pressed color removal. |  | R2 | Ritesh Jha | [5 empty] | Closed | Airfryer has pressed effect. We need to think on those scenarios.
8 | AndroidManifest.xml |  | Deepthi | versioncode has changed 102 times ? Please explain. |  | R2 | Ritesh Jha | Open | We are mainly concentrating on android:versionName="1.0.2". Because with this versionName only we are releasing apk in HockeyApps. On this versionName Android is in sync with iOS. From Release2 are are started putting versionCode=101,102……so on. In which last digits defines how many releases done in 2nd release. means 1,2.....so on. Currently verionCode is 103. Means total 3 release done to testing team. |  |  |  | Closed | We are mainly concentrating on android:versionName="1.0.2". Because with this versionName only we are releasing apk in HockeyApps. On this versionName Android is in sync with iOS. From Release2 are are started putting versionCode=101,102……so on. In which last digits defines how many releases done in 2nd release. means 1,2.....so on. Currently verionCode is 103. Means total 3 release done to testing team. |  | Open
9 | build-cfg.json |  | Deepthi | Please remove from library. |  | R2 | Ritesh Jha | Closed | Removed.
9 | build-cfg.json |  | Deepthi | Please remove from library. |  | R2 | Ritesh Jha | Removed. |  |  |  |  | Closed | removed.
10 | lint.xml |  | Deepthi | why there are so many fileds to ignore, missing translation needs to be removed because it leads to problems. Please explain for other entries. |  | R2 | Ritesh Jha | Closed | MissingTranslation removed. |  |  |  | Closed | removed MissingTranslation from lint.
11 | CDLSResponseParser | 20 | Deepthi | Remove context, it is no where used. |  | R2 | Ritesh Jha | [5 empty] | Closed | Earlier there where progess bar implemented in this class. So context was passed. While removing progress bar it was missed to remove context.
12 | CDLSResponseParser |  | Deepthi | Why this class needs to be singleton, please change. |  | R2 | Ritesh Jha | [5 empty] | Closed | Added listener to get invoked and pass data.
13 | Generic |  | Deepthi | Apply Fonts from library. |  | R2 | Ritesh Jha | [5 empty] | Closed | Copy pasted OTF files at vertical app side also. Java side added applyAttribuet api.
14 | Generic |  | Deepthi | Replacing Async task by thread and refactor the usage for http network request. |  | R2 | Naveen | [5 empty] | Closed | We have network remote interactions in 2 areas. - Interacting with CDLS - Interacting with ATOS Now both the scenario's/areas is controlled using Thread Concept.
15 | Generic |  | Deepthi | Visualise the classes conceptually and remove the places where it is having mixed responsibilities like cdlsrequesttask - Generalise the class to send network request and notify the listeners. |  | R2 | Naveen | [5 empty] | Closed | Created the Saparate Thread & removed the AsyncTask as well.
16 | Generic |  | Deepthi | Have clear responsibility for each method and class as explained and prepare the code to make it testable. |  | R2 | Ritesh & Naveen | [5 empty] | Closed | Done. Deepthi reviewed the code.
17 | Generic |  | Deepthi | Remove all the test classes and write new valid test cases atleast for logical stuff. Also replace with android junit library jar and check on jenkins on line usage. |  | R2 | Naveen & Pawan | [5 empty] | Hold | Need to write the testcase. After moving to Studio we stopped writing testcases.. Need to work on this..
18 | Generic |  | Deepthi | Move to new standard workspace name. |  | R2 | Ritesh | [5 empty] | Closed | Done
19 | Generic |  | Deepthi | Should not pass along activity between classes, use context. Please check all the classes. |  | R2 | Naveen | [5 empty] | Closed | Accompolished
20 | Generic |  | Deepthi | All parsers should not hold any response data, move to containers. Containers can hold static response data object but need not be singleton. |  | R2 | Ritesh Jha | [5 empty] | Closed | Atos and cdls parser both changed now.
21 | Generic |  | Deepthi | Do not make parsers as singleton, remove at other places if not necessary. |  | R2 | Ritesh Jha | [5 empty] | Closed | Atos and cdls parser both changed now.
22 | Generic |  | Deepthi | Initialise all menus like main menu, product menu etc in the corresponding fragments. |  | R2 | Ritesh Jha | [5 empty] | Closed | done.
23 | Generic |  | Deepthi | Move transition types like setanimation start and end to startactivity call through bundle extras. Not good to put it as configuration manager. |  | R2 | Naveen | [5 empty] | Closed | Removed the Animation Setters & Getters. Now the Animation setting mechanish is through passing the animation "id" through the launching Intent Extras.
24 | Generic |  | Deepthi | LocaleMatchService should be used to pass valid locales for cdls calls. This can be taken at last after we complete the others. |  | R2 | Naveen | [5 empty] | Closed | It is taken care.
25 | Generic |  | Deepthi | Cross check the comments given to classes and methods, some places does not make any sense and some places there is copy paste problems. |  | R2
26 | Generic |  | Deepthi | Remove unused imports in all files. |  | R2 | Naveen | [5 empty] | Closed | Accompolished.
27 | Generic |  | Deepthi | While parsing any response, check for its existence and then proceed for parsing , define fallback here too. |  | R2 | Naveen | [5 empty] | Rejected | As per the discussion with Wouter & PIM in clarification meeting, There is no callback scenario's for ATOS & CDLS.
28 | Generic |  | Deepthi | Use HttpUrlConnection class instead of HttpClient. |  | R2 | Ritesh Jha & Naveen | Hold | HttpClient and AndroidHttpClient is Deprecated since API level 22. So not recommened to use those. Link for reference https://developer.android.com/about/versions/android-5.1.html#carrier |  |  |  | Closed | HttpClient and AndroidHttpClient is Deprecated since API level 22. So not recommened to use those. Link for reference https://developer.android.com/about/versions/android-5.1.html#carrier HttpurlConnection API is used to fetch the response from CDLS as well as ATOS.
29 | Generic |  | Deepthi | Make sure it is logged properly in all places especially in all failure scenarios. |  | R2 | Naveen | [5 empty] | Closed | Done
30 | Generic |  | Deepthi | Use placeholders to form urls by using string.format(). Formation of urls should take place in corresponding fragments. Use consumercareinfo object to form the urls. |  | R2 | Naveen | [5 empty] | Closed | Accompolished Successfully
31 | Generic |  | Deepthi | List to launch individual consumercare screens from sample app can be removed. Instead we can add fields to set consumerproductinfo object, this can be taken little later. |  | R2 | Naveen | [5 empty] | Closed | Accompolished Successfully. Launcher should start with startActivity(Intent) api with if custom animation required then launcher should add in Bundle data.
32 | Generic |  | Deepthi | Tagging previouspage name and check why context data is added only for trackaction.Use placeholders to form urls by using string.format(). Formation of urls should take place in corresponding fragments. Use consumercareinfo object to form the urls. |  | R2 | Naveen | [5 empty] | Closed | Accompolished Successfully
33 | Generic |  | Deepthi | All small tasks which needs to be performed on background thread need not be present in async task, please use handler thread and handlers to post the request and response. |  | R2 | Naveen | [5 empty] | Closed | Accompolished Successfully
34 | Generic |  |  | Always post the response of background thread on UI thread so that all the places where it is received need not write extra code to run on UI thread. |  | R2 | Naveen | [5 empty] | Closed | Accompolished Successfully
35 | Generic |  | Deepthi | Remove hardcoded strings in all files. |  | R2 | Naveen | [5 empty] | Closed | HardCoded Strings removed Successfully.
36 | Generic |  | Deepthi | Do not use equalsIgnorecase for comparing menuitems from config file.please use equals. |  | R2 | Naven | [5 empty] | Closed | Changed to equals in comparing menu items,
37 | Generic |  | Deepthi | Remove all the library declarations in sample app and enable manifest merger property in sample app. |  | R2 | Naveen | [5 empty] | Closed | Manifest Merger is added successfully & Library entries removed from the launcher.
37 | DigitalCareConfigManager |  | Deepthi | combine country and language to form locale and get via single API.Move start/stop animation as part of bundle extras as mentioned earlier. |  | R2 | Naveen | [5 empty] | Closed | Now the DigitalCareManager allows setLocale, Internally DigitalCareComponenet takes the Country code & language code from the locale.
38 | DigitalCareConfigManager |  | Deepthi | getpackageName can be easily formed using context from manager, need not explicit API for that. |  | R2 | Naveen | [5 empty] | Closed | Now Hardcoded package name is removed & changed to dynamic.
39 | DigitalCareConfigManager |  | Deepthi | getAppversion is used currently only in analytics package, move as private API within that class, later on if we need only then we will move back to this class. |  | R2 | Naveen | [5 empty] | Closed | Moved successfully to AnayticsTracker file with changing access specifier to private.
40 | DigitalCareConfigManager |  | Deepthi | should remove the concept of set and get launching screen |  | R2 | Naveen | [5 empty] | Closed | Commented the Launcher SetterCode from DigitalCareConfig class
41 | DigitalCareActivity | 76 | Deepthi | requestcode is hardcoded, define globally |  | R2 | Naveen | [5 empty] | Closed | It was Facebook request Code, Now moved it to DigitaCareConstants file.
42 | AnalyticsTracker.java |  | joost.van.beek@philips.com | horizontal library should add version with every page/event tagging. |  | R3 | Ritesh | [5 empty] | Closed | Added a version with every page/event tagging. | checked on Fiddler tool to verify this version attribute.
Sstore

## Graphical Summary
Defect Classification depending on Common Cause and Defect Type
| Education | Oversight | Transcription | Communication | Input Not Clear | Input Wrong | Standard | Total No. of Defects
Assignment/Initialization | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Checking | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Algorithm/Method | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Function/Class/Object | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Timing/Serialization | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Interface/O-O Messages | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Build/Package/Merge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Documentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Relationship | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total No. of Defects | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## PI_1_Review
Defect Logging sheet Note: Please do not delete any rows/cells | [7 empty] | Update to Database | Administartive Information | [7 empty] | PHGCA47CAT | SE-IN-35MS | 24 |  | 3 |  | 12 |  | 4 |  | 3 |  | 7 | Clarified | Passed | Not Applicable | 1
Name Of Author : Deepthi |  |  |  | Review Date * | 14/09/2015 | [5 empty] | Closing remark | [5 empty] | CAT 4.x | SE-IN-3906 |  | 1 | Defect | 11 | Build/Package/Merge | 14 | Requirements Analysis | 26 | Missing | 101 | Requirements - Missed / Incomplete / Misunderstanding | Closed | Passed with Modification |  | Not Applicable | Not Applicable | 0 | 0 | 0 | 0 | 0 | 0 | 0
Work product name / Title: Consumer Care |  |  |  | Size * | [6 empty] | Authorized Signatory |  | Co-ordinator (Sign.) |  |  |  | Document | PIC |  | 2 | Investigate | 12 | Documentation | 15 | Top Level Design | 27 | Extraneous | 102 | Lack of Communication and Sync | Duplicated | Re-Review |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Version :* |  |  |  | Review Result * |  |  |  | Passed with Modification |  |  | Remarks | [5 empty] | 2012-12-17 |  |  | 3 | Suggestion/Wishful Thinking | 56 | Initialization | 16 | Component Design | 28 | Incorrect | 103 | Incomplete Design / Impact Analysis | Hold |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reviewer(s): Deepthi Shivakumar |  |  |  | Defect density * |  |  |  | 0 | [8 empty] | 4 | CL8MUHD2 |  |  |  | 108 | Logic / Algorithm / Computation Error | 17 | Implementation |  |  | 104 | Lack of Domain Knowledge | Open |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Causal Analysis | [16 empty] | 0.5 |  |  |  |  | 109 | Error Checking / Unhandled Exception / Failure Mode |  |  |  |  | 105 | Implementer Oversight / Cover Last Mile | Rejected |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | 1 |  |  |  |  | 110 | Timing / Synchronization |  |  |  |  | 106 | Lack or Improper Usage of Standards / Conventions | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Summary of Comments | [16 empty] | ICAP-PF.0003667 |  |  |  |  | 111 | Memory Management |  |  |  |  | 107 | Lack of Re-use | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Defects |  |  |  | 0 | [12 empty] | Kooloth, Sreenath |  |  |  |  | 112 | Usability / GUI | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Investigates |  |  |  | 0 | [9 empty] | . |  |  | Internal |  |  |  |  | 113 | Design / Interface | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Suggestions/ Wishful Thinking |  |  |  | 0 | [12 empty] | 2012-12-17 |  |  |  |  | 114 | Performance / Scalability
Sl. No. * | Page | Line No. | Reviewer | Description of Comment * | Severity | Release # | Owner | Comment Type * | Defect Type | Phase of Origin | Defect Qualifier | Cause of Defect | Status | Remarks | Feedback |  | Requirements Analysis |  |  |  |  | 115 | Functionality / Workflow
1 | Tagging |  | joost.van.beek@philips.com | horizontal library should add version with every page/event tagging. |  | R3 | Ritesh | [5 empty] | Closed | Added a version with every page/event tagging. |  |  | CODE1\300227886
2 | Bazaarvoice |  | Deepthi | Remove code related to image upload and download across the module. |  | R3 | Ritesh | [5 empty] | Closed
3 | BazaarReviewBean |  | Deepthi | BazaarReviewBean has to be model class under model folder |  | R3 | Ritesh | [5 empty] | Closed | Changed this structure.
4 | BazaarReviewBean |  | Deepthi | Remove unnecessary fields if it is not required |  | R3 | Ritesh | [5 empty] | Closed | Done.
5 | Bazaarvoice |  | Deepthi | Add unit test cases for wrapper classes |  | R3 | Ritesh | [7 empty] | We can add more in next release
6 | LocaleMatch |  | Deepthi | Use observer pattern to notify localematch result and then proceed with cdls/faqs etc |  | R3 | Pawan | [5 empty] | Closed | Added observer for ContactUsScreen. Ritesh has done PairProgramming with Pawan on this issue.
7 | LocaleMatch |  | Deepthi | Refactor code to take locale from LocaleMatchHandler rather than configmanager If possible. This is to add more clarity on the role of localematchhandler class. |  | R3 | Pawan | [5 empty] | Hold |  | To be taken care with next release.
8 | Bazaarvoice |  | Deepthi | Handle success and failure cases more precisely by parsing “HasErrors” field and only then invoke the callback. |  | R3 | Ritesh |  | We are mainly concentrating on android:versionName="1.0.2". Because with this versionName only we are releasing apk in HockeyApps. On this versionName Android is in sync with iOS. From Release2 are are started putting versionCode=101,102……so on. In which last digits defines how many releases done in 2nd release. means 1,2.....so on. Currently verionCode is 103. Means total 3 release done to testing team. |  |  |  | Closed | if success then ThankYou screen is launching. |  | Open
9 |  |  | Deepthi |  |  | R3 |  |  | Removed.
9 | Bazaarvoice |  | Deepthi | Complete set of API keys are not present and not handled as per locale. |  | R3 | Ritesh | [5 empty] | Open | Waiting for clarification from Aravind. | To be taken care with next release.
10 | LocaleMatch |  | Ritesh Jha | FAQ Page --> while forming URL LocalMatch is LanguageFallback based. But if we talk about other PRX calls then its country fallback. Even iOS has implemented as CountryFallback. So Aligning with iOS. Will use CountryFallback. Same logic can not be differennt for iOS and Android. |  | R3 | Pawan Deshpande |  | MissingTranslation removed. |  |  |  | Closed | Its now CountryBased.
11 | LocaleMatch |  | Ritesh Jha | for ContactUS, FAQ, Email content loading, ProgressBar is showen. But if LocaleMatch reposponse is not not avaialble then then that Progressbar is keep on showing on the screen. |  | R3 | Pawan Deshpande | [5 empty] | Closed | Adding observer pattern to notify the screens about locale received.
12 | LocaleMatchObserver |  | Ritesh Jha | synchronize(this) has to be replaced with synchronize(object). |  | R3 | Pawan Deshpande | [5 empty] | Closed | Changes addressed
13 | BazaarVoice |  | Ritesh Jha | RateAndReview-->Fragment. All classes has to be refactored with Google's standards. |  | R3 | Naveen | [5 empty] | Closed | Changes addressed
14 | BazaarVoice-> ProductreviewpreviewFragment |  | Ritesh Jha | Rating bar separate logic has not to be written. All user related inputs which added in Productwritereviewfragment class has to be passed with intent to class ProductReviewPreviewFragment |  | R3 | Ritesh | [5 empty] | Closed | Passes the serialized object.
15 | ContactUs->Call permission related |  | Pain Treatment Team | Change Call_Phone permission from Menifest, as it is blocking app download from tablet devices |  | R3 | Ritesh | [5 empty] | Closed | Replaced with <uses-feature android:name="android.hardware.telephony" android:required="false"/>
16 | BazaarVoiceWrapper |  | Deepthi | API_URL= ‘’reviews.apitestcustomer.bazaarvoice.com/bvstaging’’ is staging environment for test client, not for Philips. You can use stg.api.bazaarvoice.com for staging and api.bazaarvoice.com for production. |  | R3 | Ritesh | [5 empty] | Closed | Commit: 7b76140c62952ccf6212667a77dc7ce3b6b2155d [7b76140] Parents: 1878ad6ab1 Author: Ritesh Jha <ritesh.jha@philips.com> Date: Friday, September 25, 2015 1:29:58 PM
17 | BazaarVoiceWrapper |  | Deepthi | Remove hardcodede ClientName with API_URL |  | R3 | Ritesh | [5 empty] | Closed
18 |  |  | Naveen | Bazzar Voice code & for the name validation testing - Need testable code |  | R3 | Ritesh | [5 empty] | Closed | Added 12 test cases in support to this suggestion.
19 | BazaarVoiceWrapper |  | Deepthi | Tag name should be corresponding class name, remove "BazaarFunctions" |  | R3 | Ritesh | [5 empty] | Open |  | To be taken care with next release.
20
21 | BazaarVoiceWrapper |  | Deepthi | Remove unused variables like MIN_IMAGE_DIMENSIONS etc |  | R3 | Ritesh | [5 empty] | Closed | Refactored
22
23 | BazaarVoiceWrapper |  | Deepthi | Put appropriate logs for backend functions printing all parameters we are sending and the response we get . This helps in debugging. |  | R3 | Ritesh | [5 empty] | Open |  | To be taken care with next release.
24 | BazaarVoiceWrapper |  | Deepthi | Preview function is decided to be not used and instead we should use submit review, please cross check with ios team. |  | R3 | Ritesh | [5 empty] | Closed | calling submit now.
25 | BazaarVoice UI |  | Deepthi | Review guidance screen shows + and -, Please update to right icons if we have or provide remarks here. |  | R3 | Naveen | [5 empty] | Closed | added
26 | BazaarVoice UI |  | Deepthi | fragments package should also be moved under product review folder |  | R3 | Naveen | [5 empty] | Open | Not addressed. | To be taken care with next release.
27 | BazaarVoice UI |  | Deepthi | Email validation is not done, please use registration API |  | R3 | Naveen | [5 empty] | Closed | Done.
28 | BazaarVoice UI |  | Deepthi | Any other UI validations not done, please remove toast and provide inline validations. |  | R3 | Naveen |  | HttpClient and AndroidHttpClient is Deprecated since API level 22. So not recommened to use those. Link for reference https://developer.android.com/about/versions/android-5.1.html#carrier |  |  |  | Open | Done. | Some strings need to be validated and localized in next release.
29 | BazaarVoice UI |  | Deepthi | Remove hardcoded user id and ctn number |  | R3 | Naveen | [5 empty] | Closed | We are using user id as email id. Synced wth IOS.
30 | BazaarVoice UI |  | Deepthi | Product title and ctn number is hardcoded, please use it from consumercareproductinfo. |  | R3 | Naveen | [5 empty] | Closed | Done.
31 | ProductReviewPreviewFragment |  | Deepthi | When we proceed to thank you screen, please check the valididity of json object for null checks |  | R3 | Naveen | [5 empty] | Clarified | Never observed null object and hence not taken care. | Ok.
32 | Bazaar voice General |  | Deepthi | The error message what we display after submission is decided to show "oops something went wrong … " as we agreed with Reinoud. This also supports localization. Not sure whether localised responses we will get from bazaar voice. |  | R3 | Naveen | [5 empty] | Clarified | Done. Added available localized string, need to get localization string for recommended string y Reinoud. Synced with IOS. | To be taken care with next release.
33 | BazaarVoice UI |  | Deepthi | No of Characters validation should be done in UI. |  | R3 | Naveen | [5 empty] | Closed | Done.
34 | config.xml |  | Deepthi | Add configuration parameter for getting bazaarvoice environment and set that accordingly to bazaarvoice. |  | R3 | Deepthi | [5 empty] | Closed | Done.
35 | Terms and conditions, Bazaarvoice |  | Deepthi | Please implement T and C forming url based on country priority locale |  | R3 | Naveen | [5 empty] | Closed | Done.
36 | BazaarVoice |  | Deepthi | BazaarVoice --- response--error alert-- put some general alert synced with iOS |  | R3 | Ritesh | [5 empty] | Closed | All 4 row has been submitted together. Commit: ec46a6d05c8180a066a71826c95ae35d3cab57d3 [ec46a6d] Parents: e70cb07794 Author: Ritesh Jha <ritesh.jha@philips.com> Date: Thursday, October 01, 2015 2:17:10 PM Labels: HEAD, origin/develop, develop
37 | BazaarVoice |  | Deepthi | BazaarVoice --- if rating not accepted then put proper alert msg. Should aligned with iOS |  | R3 | Ritesh | [5 empty] | Closed
38 | BazaarVoice |  | Deepthi | BazaarVoice --- if legal terms not accepted then put proper alert msg. Should aligned with iOS |  | R3 | Ritesh | [5 empty] | Closed
39 | BazaarVoice |  | Deepthi | BazaarVoice --- if review desc is less than 50 then put proper alert msg. Should aligned with iOS |  | R3 | Ritesh | [5 empty] | Closed
40 | DigitalCare |  | Naveen | Investigate -> how to reduct the apk size from size 7MB (v2.0.0) to less |  | R3 | Ritesh | [5 empty] | Closed | As per my investigation apk size can be minimized to 1.3MB. Investigation shared with Sreenath and Aravind | Removed unwanted resources. Live_Chat.png is used as only one copy with good resolution. Style has been used for other resolution.
41 | [5 empty] | R3
42 | [5 empty] | R3
43
Sstore

## PI_2_Review
Defect Logging sheet Note: Please do not delete any rows/cells | [7 empty] | Update to Database | Administartive Information | [7 empty] | PHGCA47CAT | SE-IN-35MS | 24 |  | 3 |  | 12 |  | 4 |  | 3 |  | 7 | Clarified | Passed | Not Applicable | 1
Name Of Author : Deepthi |  |  |  | Review Date * | 2015-03-11 | [5 empty] | Closing remark | [5 empty] | CAT 4.x | SE-IN-3906 |  | 1 | Defect | 11 | Build/Package/Merge | 14 | Requirements Analysis | 26 | Missing | 101 | Requirements - Missed / Incomplete / Misunderstanding | Closed | Passed with Modification |  | Not Applicable | Not Applicable | 0 | 0 | 0 | 0 | 0 | 0 | 0
Work product name / Title: Consumer Care |  |  |  | Size * | [6 empty] | Authorized Signatory |  | Co-ordinator (Sign.) |  |  |  | Document | PIC |  | 2 | Investigate | 12 | Documentation | 15 | Top Level Design | 27 | Extraneous | 102 | Lack of Communication and Sync | Duplicated | Re-Review |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Version :* |  |  |  | Review Result * |  |  |  | Passed with Modification |  |  | Remarks | [5 empty] | 2012-12-17 |  |  | 3 | Suggestion/Wishful Thinking | 56 | Initialization | 16 | Component Design | 28 | Incorrect | 103 | Incomplete Design / Impact Analysis | Hold |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reviewer(s): Deepthi Shivakumar |  |  |  | Defect density * |  |  |  | 0 | [8 empty] | 4 | CL8MUHD2 |  |  |  | 108 | Logic / Algorithm / Computation Error | 17 | Implementation |  |  | 104 | Lack of Domain Knowledge | Open |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Causal Analysis | [16 empty] | 0.5 |  |  |  |  | 109 | Error Checking / Unhandled Exception / Failure Mode |  |  |  |  | 105 | Implementer Oversight / Cover Last Mile | Rejected |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | 1 |  |  |  |  | 110 | Timing / Synchronization |  |  |  |  | 106 | Lack or Improper Usage of Standards / Conventions | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Summary of Comments | [16 empty] | ICAP-PF.0003667 |  |  |  |  | 111 | Memory Management |  |  |  |  | 107 | Lack of Re-use | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Defects |  |  |  | 0 | [12 empty] | Kooloth, Sreenath |  |  |  |  | 112 | Usability / GUI | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Investigates |  |  |  | 0 | [9 empty] | . |  |  | Internal |  |  |  |  | 113 | Design / Interface | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Suggestions/ Wishful Thinking |  |  |  | 0 | [12 empty] | 2012-12-17 |  |  |  |  | 114 | Performance / Scalability
Sl. No. * | Page | Line No. | Reviewer | Description of Comment * | Severity | Release # | Owner | Comment Type * | Defect Type | Phase of Origin | Defect Qualifier | Cause of Defect | Status | Remarks | Feedback |  | Requirements Analysis |  |  |  |  | 115 | Functionality / Workflow
1 | PRX client library |  | Deepthi | Create subclass of builder inside library , not on vertical side |  | PI2 | Naveen | [9 empty] | CODE1\300227886
2 | PRX client library |  | Deepthi | Use builder subclass to create request url and also form the response object |  | PI2 | Naveen
3 | PRX client library |  | Deepthi | Put all generic inputs like locale, sector and catalog code to base PrxDatabuilder class |  | PI2 | Naveen
4 | PRX client library |  | Deepthi | Remove requestTag from builder subclass and move it to parent class |  | PI2 | Naveen
5 | PRX client library |  | Deepthi | Remove the code inside ResponseData where it is checking for builder type/instance and based on this , it is invoking respective model. Example getAssetModel() where it checks builder instance for asset type |  | PI2 | Naveen
6 | PRX client library |  | Deepthi | Introduce abstract parseResponse method inside ResponseData and make the class abstract |  | PI2 | Naveen
7 | PRX client library |  | Deepthi | Please pass along the responseData model object along with onResponseSuccess callback |  | PI2 | Naveen
8 | PRX client library |  | Deepthi | Instead of passing error as string, please create error class and build error message and error code which comes from volley and propogate back in onResponseError callback. |  | PI2 | Naveen |  | We are mainly concentrating on android:versionName="1.0.2". Because with this versionName only we are releasing apk in HockeyApps. On this versionName Android is in sync with iOS. From Release2 are are started putting versionCode=101,102……so on. In which last digits defines how many releases done in 2nd release. means 1,2.....so on. Currently verionCode is 103. Means total 3 release done to testing team. | [6 empty] | Open
9 | PRX client library |  | Deepthi | Remove parameters like requestbuilder, responselistener from init method of requestmanager and move it to executeJsonObjectRequest |  | PI2 | Naveen |  | Removed.
9 | PRX client library |  | Deepthi | Have explicit methods for each type of request like jsonobject request, string request etc |  | PI2 | Naveen
10 | Consumer care |  | Deepthi | Put debug log statements in callback to know the response status from prx component. |  | PI2 | Naveen |  | MissingTranslation removed.
11 | Consumer care |  | Deepthi | Hit Localematch and PRX summary call initially in home screen and until that we shall show progress indicator. This is because we need summary response for our 2 features and have that decision much before to avoid problems on click of that feature. |  | PI2 | Naveen
12 | Consumer care |  | Deepthi | I think most of the app uses intent to launch app to view pdf and we may face problems using webview, please change back to intent approach. |  | PI2 | Ritesh
13 | Consumer care |  | Deepthi | Please remove all hardcoded data and pick from consumerproductinfo class inside viewproductmodel class. |  | PI2 | Naveen
14 | Consumer care |  | Deepthi | Remove PRX callback from viewproductdetail model and just use validation which is done in home screen. |  | PI2 | Naveen
15 | Consumer care |  | Deepthi | Please tinypng.com and optimise chatnow image rather than creating single 9 patch image for all resolutions since Reinoud said not good to have 9patch image. |  | PI2 | Ritesh
16 | productdetailfragment |  | Deepthi | updateViewsWithData(), no data available is shown, I think it wont be clear to user |  | PI2
17 | productdetailfragment |  | Deepthi | manual link, check for pdf extension and type as qsg , if it is not there please check usermanual . Both are not there, pls remove that button. |  | PI2
18 | productdetailfragment |  |  | VIEWPRODUCTDETAILS_PRX_ASSETS_VIDEO_URL and other constants which are used inside product detail screen , please define it local. |  | PI2
19 | productdetailfragment |  | Deepthi | Please don’t set viewproductdata model in digitalcareconfigmanager class.check the feasibility if we can move to differemnt place . |  | PI2
20 | productdetailfragment |  |  | why open interactive manual option is still there? |  | PI2
21 | productdetailfragment |  | Deepthi | rename "anfe" variable in pdfdownloader |  | PI2
22 | productdetailfragment |  |  | actionbar title is same for both product detail fragment and philipspagefragment. |  | PI2
23 | productdetailfragment |  | Deepthi | Why faq pagename is set as previous page name inside philipspagefragment |  | PI2
24 | productdetailfragment |  | Deepthi | Cant we give pdf url link to while launching intent to open pdf instead of downloading manually and creating an async task? Please provide remarks. |  | PI2
25 |  |  | Deepthi
26 |  |  | Deepthi
27 |  |  | Deepthi
28 |  |  | Deepthi | [5 empty] | HttpClient and AndroidHttpClient is Deprecated since API level 22. So not recommened to use those. Link for reference https://developer.android.com/about/versions/android-5.1.html#carrier
29 |  |  | Deepthi
30 |  |  | Deepthi
31 |  |  | Deepthi
32 |  |  | Deepthi
33 |  |  | Deepthi
34 |  |  | Deepthi
35 |  |  | Deepthi
36 |  |  | Deepthi
37 |  |  | Deepthi
38 |  |  | Deepthi
39 |  |  | Deepthi
40 |  |  | Naveen
41
42
43
Sstore