## Review_Record
Defect Logging sheet Note: Please do not delete any rows/cells | [7 empty] | Update to Database | Administartive Information | [7 empty] | PHGCA47CAT | SE-IN-35MS | 24 |  | 3 |  | 12 |  | 4 |  | 3 |  | 7 | Clarified | Passed | Not Applicable | 1
Name Of Author : Deepthi |  |  |  | Review Date * |  |  | 2015-08-06 |  |  |  | Closing remark | [5 empty] | CAT 4.x | SE-IN-3906 |  | 1 | Defect | 11 | Build/Package/Merge | 14 | Requirements Analysis | 26 | Missing | 101 | Requirements - Missed / Incomplete / Misunderstanding | Closed | Passed with Modification |  | Not Applicable | Not Applicable | 0 | 0 | 0 | 0 | 0 | 0 | 0
Work product name / Title: Consumer Care |  |  |  | Size * | [6 empty] | Authorized Signatory |  | Co-ordinator (Sign.) |  |  |  | Document | PIC |  | 2 | Investigate | 12 | Documentation | 15 | Top Level Design | 27 | Extraneous | 102 | Lack of Communication and Sync | Duplicated | Re-Review |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Version :* |  |  |  | Review Result * |  |  |  | Passed with Modification |  |  | Remarks | [5 empty] | 2012-12-17 |  |  | 3 | Suggestion/Wishful Thinking | 56 | Initialization | 16 | Component Design | 28 | Incorrect | 103 | Incomplete Design / Impact Analysis | Hold |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reviewer(s): Deepthi Shivakumar |  |  |  | Defect density * |  |  |  | 0 | [8 empty] | 4 | CL8MUHD2 |  |  |  | 108 | Logic / Algorithm / Computation Error | 17 | Implementation |  |  | 104 | Lack of Domain Knowledge | Open |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Causal Analysis | [16 empty] | 0.5 |  |  |  |  | 109 | Error Checking / Unhandled Exception / Failure Mode |  |  |  |  | 105 | Implementer Oversight / Cover Last Mile | Rejected |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | 1 |  |  |  |  | 110 | Timing / Synchronization |  |  |  |  | 106 | Lack or Improper Usage of Standards / Conventions | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Summary of Comments | [16 empty] | ICAP-PF.0003667 |  |  |  |  | 111 | Memory Management |  |  |  |  | 107 | Lack of Re-use | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Defects |  |  |  | 0 | [12 empty] | Kooloth, Sreenath |  |  |  |  | 112 | Usability / GUI | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Investigates |  |  |  | 0 | [9 empty] | . |  |  | Internal |  |  |  |  | 113 | Design / Interface | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Suggestions/ Wishful Thinking |  |  |  | 0 | [12 empty] | 2012-12-17 |  |  |  |  | 114 | Performance / Scalability
Sl. No. * | Page | Line No. | Reviewer | Description of Comment * | Severity | Release # | Owner | Comment Type * | Defect Type | Phase of Origin | Defect Qualifier | Cause of Defect | Status | Remarks | Feedback |  | Requirements Analysis |  |  |  |  | 115 | Functionality / Workflow
1 | Utils | 61 | Deepthi | Activity context or activity is not necessary to take telephony manager. Use application context from configurationManager. |  | R2 | Naveen | [5 empty] | Closed | Saparate dedicated receiver is added to get ConnectionChanges. + Need to check by removing receiver in Manifest File |  |  | CODE1\300227886
2 | Utils | 54 | Deepthi | isEmpty() method does not make sense, inline the method. |  | R2 | Naveen | [5 empty] | Closed | Removed from the Utils.java & added inline.
3 | Utils |  | Deepthi | isTablet () and isNetworkConnected- Use application context from configurationManager. |  | R2 | Naveen | [5 empty] | Closed | Replaced with ApplicationContext from Activity parameter.
4 | Utils |  | Deepthi | In general, it seems to be a network utility, rename, don’t mix functionalities . Remove commented out. |  | R2 | Naveen | [5 empty] | Closed | Naming convention followed.
5 | CallFeature |  | Deepthi | This is reduntant and useless and remove comparision code used in unit test case (DigitalCareActivityTest,java) |  | R2 | Naveen | [5 empty] | Closed | Removed the testcases developed with reference to the class coverge report.
6 | DeviceType |  | Deepthi | This is reduntant and not used, pls remove this class. |  | R2 | Naveen | [5 empty] | Closed | Removed the redundant method successfully.
7 | DigitalCare_Config.xml |  | Deepthi | Adapting new config file changes and no extra changes should be seen except hamburger menu pressed color removal. |  | R2 | Ritesh Jha | [5 empty] | Closed | Airfryer has pressed effect. We need to think on those scenarios.
8 | AndroidManifest.xml |  | Deepthi | versioncode has changed 102 times ? Please explain. |  | R2 | Ritesh Jha | Open | We are mainly concentrating on android:versionName="1.0.2". Because with this versionName only we are releasing apk in HockeyApps. On this versionName Android is in sync with iOS. From Release2 are are started putting versionCode=101,102……so on. In which last digits defines how many releases done in 2nd release. means 1,2.....so on. Currently verionCode is 103. Means total 3 release done to testing team. |  |  |  | Closed | We are mainly concentrating on android:versionName="1.0.2". Because with this versionName only we are releasing apk in HockeyApps. On this versionName Android is in sync with iOS. From Release2 are are started putting versionCode=101,102……so on. In which last digits defines how many releases done in 2nd release. means 1,2.....so on. Currently verionCode is 103. Means total 3 release done to testing team. |  | Open
9 | build-cfg.json |  | Deepthi | Please remove from library. |  | R2 | Ritesh Jha | Closed | Removed.
9 | build-cfg.json |  | Deepthi | Please remove from library. |  | R2 | Ritesh Jha | Removed. |  |  |  |  | Closed | removed.
10 | lint.xml |  | Deepthi | why there are so many fileds to ignore, missing translation needs to be removed because it leads to problems. Please explain for other entries. |  | R2 | Ritesh Jha | Closed | MissingTranslation removed. |  |  |  | Closed | removed MissingTranslation from lint.
11 | CDLSResponseParser | 20 | Deepthi | Remove context, it is no where used. |  | R2 | Ritesh Jha | [5 empty] | Closed | Earlier there where progess bar implemented in this class. So context was passed. While removing progress bar it was missed to remove context.
12 | CDLSResponseParser |  | Deepthi | Why this class needs to be singleton, please change. |  | R2 | Ritesh Jha | [5 empty] | Closed | Added listener to get invoked and pass data.
13 | Generic |  | Deepthi | Apply Fonts from library. |  | R2 | Ritesh Jha | [5 empty] | Closed | Copy pasted OTF files at vertical app side also. Java side added applyAttribuet api.
14 | Generic |  | Deepthi | Replacing Async task by thread and refactor the usage for http network request. |  | R2 | Naveen | [5 empty] | Closed | We have network remote interactions in 2 areas. - Interacting with CDLS - Interacting with ATOS Now both the scenario's/areas is controlled using Thread Concept.
15 | Generic |  | Deepthi | Visualise the classes conceptually and remove the places where it is having mixed responsibilities like cdlsrequesttask - Generalise the class to send network request and notify the listeners. |  | R2 | Naveen | [5 empty] | Closed | Created the Saparate Thread & removed the AsyncTask as well.
16 | Generic |  | Deepthi | Have clear responsibility for each method and class as explained and prepare the code to make it testable. |  | R2 | Ritesh & Naveen | [5 empty] | Closed | Done. Deepthi reviewed the code.
17 | Generic |  | Deepthi | Remove all the test classes and write new valid test cases atleast for logical stuff. Also replace with android junit library jar and check on jenkins on line usage. |  | R2 | Naveen & Pawan | [5 empty] | Hold | Need to write the testcase. After moving to Studio we stopped writing testcases.. Need to work on this..
18 | Generic |  | Deepthi | Move to new standard workspace name. |  | R2 | Ritesh | [5 empty] | Closed | Done
19 | Generic |  | Deepthi | Should not pass along activity between classes, use context. Please check all the classes. |  | R2 | Naveen | [5 empty] | Closed | Accompolished
20 | Generic |  | Deepthi | All parsers should not hold any response data, move to containers. Containers can hold static response data object but need not be singleton. |  | R2 | Ritesh Jha | [5 empty] | Closed | Atos and cdls parser both changed now.
21 | Generic |  | Deepthi | Do not make parsers as singleton, remove at other places if not necessary. |  | R2 | Ritesh Jha | [5 empty] | Closed | Atos and cdls parser both changed now.
22 | Generic |  | Deepthi | Initialise all menus like main menu, product menu etc in the corresponding fragments. |  | R2 | Ritesh Jha | [5 empty] | Closed | done.
23 | Generic |  | Deepthi | Move transition types like setanimation start and end to startactivity call through bundle extras. Not good to put it as configuration manager. |  | R2 | Naveen | [5 empty] | Closed | Removed the Animation Setters & Getters. Now the Animation setting mechanish is through passing the animation "id" through the launching Intent Extras.
24 | Generic |  | Deepthi | LocaleMatchService should be used to pass valid locales for cdls calls. This can be taken at last after we complete the others. |  | R2 | Naveen | [5 empty] | Closed | It is taken care.
25 | Generic |  | Deepthi | Cross check the comments given to classes and methods, some places does not make any sense and some places there is copy paste problems. |  | R2
26 | Generic |  | Deepthi | Remove unused imports in all files. |  | R2 | Naveen | [5 empty] | Closed | Accompolished.
27 | Generic |  | Deepthi | While parsing any response, check for its existence and then proceed for parsing , define fallback here too. |  | R2 | Naveen | [5 empty] | Rejected | As per the discussion with Wouter & PIM in clarification meeting, There is no callback scenario's for ATOS & CDLS.
28 | Generic |  | Deepthi | Use HttpUrlConnection class instead of HttpClient. |  | R2 | Ritesh Jha & Naveen | Hold | HttpClient and AndroidHttpClient is Deprecated since API level 22. So not recommened to use those. Link for reference https://developer.android.com/about/versions/android-5.1.html#carrier |  |  |  | Closed | HttpClient and AndroidHttpClient is Deprecated since API level 22. So not recommened to use those. Link for reference https://developer.android.com/about/versions/android-5.1.html#carrier HttpurlConnection API is used to fetch the response from CDLS as well as ATOS.
29 | Generic |  | Deepthi | Make sure it is logged properly in all places especially in all failure scenarios. |  | R2 | Naveen | [5 empty] | Closed | Done
30 | Generic |  | Deepthi | Use placeholders to form urls by using string.format(). Formation of urls should take place in corresponding fragments. Use consumercareinfo object to form the urls. |  | R2 | Naveen | [5 empty] | Closed | Accompolished Successfully
31 | Generic |  | Deepthi | List to launch individual consumercare screens from sample app can be removed. Instead we can add fields to set consumerproductinfo object, this can be taken little later. |  | R2 | Naveen | [5 empty] | Closed | Accompolished Successfully. Launcher should start with startActivity(Intent) api with if custom animation required then launcher should add in Bundle data.
32 | Generic |  | Deepthi | Tagging previouspage name and check why context data is added only for trackaction.Use placeholders to form urls by using string.format(). Formation of urls should take place in corresponding fragments. Use consumercareinfo object to form the urls. |  | R2 | Naveen | [5 empty] | Closed | Accompolished Successfully
33 | Generic |  | Deepthi | All small tasks which needs to be performed on background thread need not be present in async task, please use handler thread and handlers to post the request and response. |  | R2 | Naveen | [5 empty] | Closed | Accompolished Successfully
34 | Generic |  |  | Always post the response of background thread on UI thread so that all the places where it is received need not write extra code to run on UI thread. |  | R2 | Naveen | [5 empty] | Closed | Accompolished Successfully
35 | Generic |  | Deepthi | Remove hardcoded strings in all files. |  | R2 | Naveen | [5 empty] | Closed | HardCoded Strings removed Successfully.
36 | Generic |  | Deepthi | Do not use equalsIgnorecase for comparing menuitems from config file.please use equals. |  | R2 | Naven | [5 empty] | Closed | Changed to equals in comparing menu items,
37 | Generic |  | Deepthi | Remove all the library declarations in sample app and enable manifest merger property in sample app. |  | R2 | Naveen | [5 empty] | Closed | Manifest Merger is added successfully & Library entries removed from the launcher.
37 | DigitalCareConfigManager |  | Deepthi | combine country and language to form locale and get via single API.Move start/stop animation as part of bundle extras as mentioned earlier. |  | R2 | Naveen | [5 empty] | Closed | Now the DigitalCareManager allows setLocale, Internally DigitalCareComponenet takes the Country code & language code from the locale.
38 | DigitalCareConfigManager |  | Deepthi | getpackageName can be easily formed using context from manager, need not explicit API for that. |  | R2 | Naveen | [5 empty] | Closed | Now Hardcoded package name is removed & changed to dynamic.
39 | DigitalCareConfigManager |  | Deepthi | getAppversion is used currently only in analytics package, move as private API within that class, later on if we need only then we will move back to this class. |  | R2 | Naveen | [5 empty] | Closed | Moved successfully to AnayticsTracker file with changing access specifier to private.
40 | DigitalCareConfigManager |  | Deepthi | should remove the concept of set and get launching screen |  | R2 | Naveen | [5 empty] | Closed | Commented the Launcher SetterCode from DigitalCareConfig class
41 | DigitalCareActivity | 76 | Deepthi | requestcode is hardcoded, define globally |  | R2 | Naveen | [5 empty] | Closed | It was Facebook request Code, Now moved it to DigitaCareConstants file.
42 | AnalyticsTracker.java |  | joost.van.beek@philips.com | horizontal library should add version with every page/event tagging. |  | R3 | Ritesh | [5 empty] | Closed | Added a version with every page/event tagging. | checked on Fiddler tool to verify this version attribute.
Sstore

## Graphical Summary
Defect Classification depending on Common Cause and Defect Type
| Education | Oversight | Transcription | Communication | Input Not Clear | Input Wrong | Standard | Total No. of Defects
Assignment/Initialization | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Checking | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Algorithm/Method | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Function/Class/Object | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Timing/Serialization | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Interface/O-O Messages | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Build/Package/Merge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Documentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Relationship | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total No. of Defects | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## PI2_Review
Defect Logging sheet Note: Please do not delete any rows/cells | [7 empty] | Update to Database | Administartive Information | [7 empty] | PHGCA47CAT | SE-IN-35MS | 24 |  | 3 |  | 12 |  | 4 |  | 3 |  | 7 | Clarified | Passed | Not Applicable | 1
Name Of Author : Deepthi |  |  |  | Review Date * | 17/03/2016 | [5 empty] | Closing remark | [5 empty] | CAT 4.x | SE-IN-3906 |  | 1 | Defect | 11 | Build/Package/Merge | 14 | Requirements Analysis | 26 | Missing | 101 | Requirements - Missed / Incomplete / Misunderstanding | Closed | Passed with Modification |  | Not Applicable | Not Applicable | 0 | 0 | 0 | 0 | 0 | 0 | 0
Work product name / Title: Product Registration |  |  |  | Size * | [6 empty] | Authorized Signatory |  | Co-ordinator (Sign.) |  |  |  | Document | PIC |  | 2 | Investigate | 12 | Documentation | 15 | Top Level Design | 27 | Extraneous | 102 | Lack of Communication and Sync | Duplicated | Re-Review |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Version :* |  |  |  | Review Result * |  |  |  | Passed with Modification |  |  | Remarks | [5 empty] | 2012-12-17 |  |  | 3 | Suggestion/Wishful Thinking | 56 | Initialization | 16 | Component Design | 28 | Incorrect | 103 | Incomplete Design / Impact Analysis | Hold |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reviewer(s): Deepthi Shivakumar, Matthijs |  |  |  | Defect density * |  |  |  | 0 | [8 empty] | 4 | CL8MUHD2 |  |  |  | 108 | Logic / Algorithm / Computation Error | 17 | Implementation |  |  | 104 | Lack of Domain Knowledge | Open |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Causal Analysis | [16 empty] | 0.5 |  |  |  |  | 109 | Error Checking / Unhandled Exception / Failure Mode |  |  |  |  | 105 | Implementer Oversight / Cover Last Mile | Rejected |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | 1 |  |  |  |  | 110 | Timing / Synchronization |  |  |  |  | 106 | Lack or Improper Usage of Standards / Conventions | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Summary of Comments | [16 empty] | ICAP-PF.0003667 |  |  |  |  | 111 | Memory Management |  |  |  |  | 107 | Lack of Re-use | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Defects |  |  |  | 0 | [12 empty] | Kooloth, Sreenath |  |  |  |  | 112 | Usability / GUI | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Investigates |  |  |  | 0 | [9 empty] | . |  |  | Internal |  |  |  |  | 113 | Design / Interface | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Suggestions/ Wishful Thinking |  |  |  | 0 | [12 empty] | 2012-12-17 |  |  |  |  | 114 | Performance / Scalability
Sl. No. * | Page | Line No. | Reviewer | Description of Comment * | Severity | Release # | Owner | Comment Type * | Defect Type | Phase of Origin | Defect Qualifier | Cause of Defect | Status | Remarks | Feedback |  | Requirements Analysis |  |  |  |  | 115 | Functionality / Workflow
1 | Prod Reg demo app |  | Deepthi | prodlog - should not exist in sample app. just use framwork log statmenets.. Also move this logger to prod reg lib. |  | PI2 | Kiran | [5 empty] | Closed |  |  |  | CODE1\300227886
2 | Prod Reg demo app |  | Deepthi | import com.philips.cdp.registration.ui.utils.RLog; .. remove usage of this class inside demo app. |  | PI2 | Kiran | [5 empty] | Closed
3 | General |  | Deepthi | Tag names should not be localised.. define member variable called TAGNAME.. it should be this.getClass().getSimpleName() |  | PI2 | Kiran | [5 empty] | Closed
4 | General |  | Deepthi | Dont hardcode any strings locally. |  | PI2 | Kiran | [5 empty] | Closed
5 | Prod Reg demo app |  | Deepthi | Extract initilaization of user registration into a separate method. |  | PI2 | Kiran | [5 empty] | Closed
6 | Prod Reg demo app |  | Deepthi | Prefix with "m" for all member variables preferably. |  | PI2 | Kiran | [5 empty] | Closed
7 | Prod Reg demo app |  | Deepthi | Prxlogger enabling remove from demo app |  | PI2 | Kiran | [5 empty] | Closed
8 | Prod Reg demo app |  | Deepthi | ResponseListener of PRX should not be used by demo app, create a own ProdRegLiistener class and add success and failure methods.. onProdRegfailure(ProdRegError error).. ProdRegError is an enum with error codes and strings as mentioned in email. | Major | PI2 | Kiran | [5 empty] | Closed |  |  | Open
9 | Prod Reg demo app |  | Deepthi | Rename ProductResponse to ProdRegResponse, registeredProducts to getRegisteredProducts |  | PI2 | Kiran | [5 empty] | Closed
9 | Prod Reg demo app |  | Deepthi | date validation to move to library , remove changes from demo app. |  | PI2 | Kiran | [5 empty] | Closed
10 | Prod Reg demo app |  | Deepthi |  |  | PI2 | Kiran | [5 empty] | Closed
11 | Prod Reg Lib |  | Deepthi | Create Error Handler classes and propagate accordingly- |  | PI3 | Kiran | [5 empty] | Closed
12 | Prod Reg Lib |  | Deepthi | change response success with out parameters for prod registration |  | PI3 | Yogesh | [5 empty] | Closed
13 | Prod Reg Lib |  | Deepthi | remove sector and catalog from constructor of UP |  | PI3 | Yogesh | [5 empty] | Closed
14 | Prod Reg Lib |  | Deepthi | create constants on dedicated classes |  | PI3 | Yogesh | [5 empty] | Closed
15 | Prod Reg Lib |  | Deepthi | add functionlaity is user registered locally to RP |  | PI3 | Yogesh | [5 empty] | Closed
16 | Prod Reg Lib |  | Deepthi | add registration validation wrt uuid |  | PI3 | Yogesh | [5 empty] | Closed
17 | Prod Reg Lib |  | Deepthi | process cached products only for current uuid |  | PI3 | Yogesh | [5 empty] | Closed
18 | Prod Reg Lib |  | Deepthi | Add configuration in all request class for production |  | PI3 | Kiran | [5 empty] | Closed
19 | Prod Reg Lib |  | Deepthi | on Registrattion failed give a call back with parameterized RP |  | PI3 | Yogesh | [5 empty] | Closed
20 | Prod Reg Lib |  | Deepthi | Dont validate date if it is null |  | PI3 | Yogesh | [5 empty] | Closed
21 | Prod Reg Lib |  | Deepthi | arranging proper error code with id |  | PI3 | Kiran | [5 empty] | Closed
22 | PRX Clint lib |  | Deepthi | prxdatebuilder packge name to Requests and prxdatmodel to datmodels |  | PI3 | Kiran | [5 empty] | Closed
23 | PRX Clint lib |  | Deepthi | make var into m prefix remove m prefix in APIs setters and getters sector, catalog - both inputs are taken as string now, change to localematch enums Sector, Catalog |  | PI3 | Kiran | [5 empty] | Closed
24 | PRX Clint lib |  | Deepthi | Error class as enum in prx clint |  | PI3 | Kiran | [5 empty] | Closed
25 | PRX Clint lib |  | Deepthi | PrxJsonRequest , RequestType move to request package and SSLCertificateManager move to network package |  | PI3 | Kiran | [5 empty] | Closed
26 | PRX Clint lib |  | Deepthi | in RequestManager class need added setLocale(), added local in dependency ( compile 'com.philips.cdp:localeMatch:1.1.1') |  | PI3 | Kiran | [5 empty] | Closed
27 | PRX Clint lib |  | Deepthi | to add register and unregister call backs |  | PI3 | Kiran | [5 empty] | Closed
28 | PRX Clint lib |  | Deepthi | to throw run time exception when listner null |  | PI3 | Yogesh | [5 empty] | Closed
29 | PRX Clint lib |  | Deepthi | API name and package name changes |  | PI3 | Yogesh | [5 empty] | Open
30 | PRX Clint lib |  | Deepthi | To modify getting registered products list as per iOS |  | PI3 | Yogesh | [5 empty] | Open
31
32
33
34
35
36
37
38
39
40
41 | [5 empty] | R3
42 | [5 empty] | R3
43
Sstore