## Avaiability
Sprint Planning |  | Day | David | Louis | Natalia | Rainer | Member | Member | Member | Member | Member | Total Hours | Total SP | Corrected Hours
|  | Monday | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 24 | 2.025 | 19.2
Project | Shine | Tuesday | 8 | 8 | 8 | 7 | 0 | 0 | 0 | 0 | 0 | 31 | 2.6156 | 24.8
Sprint | 16.1.4 | Wednesday | 8 | 8 | 8 | 7 | 0 | 0 | 0 | 0 | 0 | 31 | 2.6156 | 24.8
|  | Thursday | 4 | 8 | 8 | 7 | 0 | 0 | 0 | 0 | 0 | 27 | 2.2781 | 21.6
Team size | 4 | Friday | 8 | 0 | 8 | 7 | 0 | 0 | 0 | 0 | 0 | 23 | 1.9406 | 18.4
Sprint length in weeks | 2 | Monday | 8 | 8 | 8 | 7 | 0 | 0 | 0 | 0 | 0 | 31 | 2.6156 | 24.8
|  | Tuesday | 8 | 8 | 8 | 7 | 0 | 0 | 0 | 0 | 0 | 31 | 2.6156 | 24.8
Base Team Velocity | 27 | Wednesday | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 32 | 2.7 | 25.6
Team member 1 week velocity | 3.375 | Thursday | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 32 | 2.7 | 25.6
Team member 1 hour velocity | 0.084375 | Friday | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 24 | 2.025 | 19.2
Team availability | 89.38% | Totals | 68 | 64 | 80 | 74 | 0 | 0 | 0 | 0 | 0 | 286 | 24.1313 | 228.8
Available velocity | 24.1313
Committed velocity
Hour correction factor | 0.8
Initial Task estimation | 130
Percentage for Support | 30%

## Burndown Data
Tasks | 160.16 | 152 |  |  |  | Total
Day of sprint | Available | Estimated | Burned | Remaining | Task Delay | Unplanned | Delay
Sprint Start | 13.44 | 152 | 0 | 152 | 0 | 0 | 0
Tuesday | 17.36 | 138.56 | 5 | 147 | 8.44 | 0 | 8.44
Wednesday | 17.36 | 121.2 | 28 | 119 | -2.2 | 0 | -2.2
Thursday | 15.12 | 103.84 | 16 | 103 | -0.84 | 0 | -0.84
Friday | 12.88 | 88.72 | 10 | 93 | 4.28 | 0 | 4.28
Monday | 17.36 | 75.84 |  |  | #N/A | 0 | #N/A
Tuesday | 17.36 | 58.48 |  |  | #N/A | 0 | #N/A
Wednesday | 17.92 | 41.12 |  |  | #N/A | 0 | #N/A
Thursday | 17.92 | 23.2 |  |  | #N/A | 0 | #N/A
Friday | 13.44 | 5.28 |  |  | #N/A | 0 | #N/A
Sprint End | 0 | 0 |  |  | #N/A | 0 | #N/A
Support | 76.8 | 0
Day of sprint | Available | Burned Total | Burned | Remaining | Max
Sprint Start | 0 | 0 | 0 | 76.8 | 76.8
Tuesday | 0 | 8 | 8 | 68.8 | 76.8
Wednesday | 0 | 10 | 2 | 66.8 | 76.8
Thursday | 0 | 16 | 6 | 60.8 | 76.8
Friday | 0 | 19 | 3 | 57.8 | 76.8
Monday | 0 |  |  |  | 76.8
Tuesday | 0 |  |  |  | 76.8
Wednesday | 0 |  |  |  | 76.8
Thursday | 0 |  |  |  | 76.8
Friday | 0 |  |  |  | 76.8
Sprint End | 0 |  |  |  | 76.8

## Burndown Chart
Shine | Sprint Burndown | Sprint | 16.1.4 | Velocity (SP) | ? | Todo (H) | 152

## Support Chart
Shine | Support Burnup | Sprint | 16.1.4 | Max | 76.8 | Spend | 8 | Remaining | 57.8