## Title Page
Purpose
This Document Review Sheet template is used during formal document reviews to capture the reviewer's feedback.
Scope
Document: CML000003 Test Protocol BlueLib Product/Platform: CommLib/CDP2 Platform

## Logging
Feedback logging sheet
Note: Severity: "Defect=D", "Editorial=E" or "Question=Q"
Page # | Line # | Description | Reviewer | Severity | Solved (Y/N) | Argumentation | Verified? (Y/N)
5 | Chapter 2 | Not "test scenarios shall meet the requirements" but "test scenarios shall test if the requirements are met" | B. Flaton | D | Y | Sentence improved | Y
5 | Chapter 4 | Say something about used Phones during testing | B. Flaton | D | Y | infromation added | Y
5 | Chapter 5 | Discribe test setup details (distance between phone/peripheral, other peripherals nearby, etc) here, not in individual tests | B. Flaton | E | Y | infromation about distance added | Y
9 | test 14869 | Replace the Test.Product.InvalidHeaderVersion.upg with something like "firmware image with invalid header" | B. Flaton | E | Y | Test case title updated | Y
9 | test 14870 | similar to previous remark | B. Flaton | E | Y | Test case title updated, also updated tests 14867 and 14873 | Y
5 | Chapter 4 | Test Set-up should mention something about a Product Stub running on a windows machine. | R. Schlönvoigt | D | Y | information added | Y